## Schedule
Task# | Description | Start Date | End Date | Duration in Days | Days Passed | Days Left | Effort Hours Estimate | Effort Hours Complete | Effort Hours Left | Input | Output | Responsible | Status
| Total --> |  |  | 394 | 48 | 0 | 390 | 390 | 0
000 | Project Start and End Dates | 2021-02-24 | 2021-04-13 | 48 |  | 0
001 | Develop Methodology | 2021-02-15 | 2021-02-24 | 9 |  |  | 5 | 5 | 0 | Brainstorm ideas, project description | Design process and goals | Everyone | Complete
002 | Requirements and tool gathering | 2021-02-20 | 2021-03-03 | 11 |  |  | 10 | 10 | 0 | Project needs and methodology | IDE to use, list of goals, schedule | Everyone | Complete
002a | Functionality and Requirements Documents | 2020-03-01 | 2020-03-09 | 8 |  |  | 7 | 7 | 0 | Requirements and tools gathered. | Functionality Document, System Requirements Documnet | Ethan | Complete
003 | Design (diagrams, workflow) | 2021-02-21 | 2021-03-10 | 17 |  |  | 15 | 15 | 0 | Project description, requirements, functionality | Blueprint of system | Everyone | Complete
003a | Sequence Diagram | 2020-03-01 | 2020-03-09 | 8 |  |  | 5 | 5 | 0 | Users and user functions | Sequence Diagram | Mikey | Complete
003b | Workflow Diagram | 2020-03-01 | 2020-03-09 | 8 |  |  | 5 | 5 | 0 | Users and user functions | Workflow Diagram | Jiovany | Complete
003c | UML Diagram | 2020-03-01 | 2020-03-09 | 8 |  |  | 5 | 5 | 0 | Design overview and classes | UML Diagram | Nick | Complete
004 | Implement Reffering Dr section | 2021-03-10 | 2021-03-17 | 7 |  |  | 47 | 47 | 0 | Functionality Document, Sequence Diagram, Workflow Diagram , UML Diagram | Referring Dr. section | Ethan | Complete
004a | Create Referring Dr. obejct // inherit from user | 2021-03-10 | 2021-03-17 | 7 |  |  | 5 | 5 | 0 | Functionality Document, Sequence Diagram, Workflow Diagram , UML Diagram | Dr. Object. Drs that log into the system |  | Complete
004b | Create Patient object | 2021-03-10 | 2021-03-17 | 7 |  |  | 3 | 3 | 0 | Functionality Document, Sequence Diagram, Workflow Diagram , UML Diagram | Patient Object that be used within the order object. will be viewd by each subsequent user |  | Complete
004c | Create order object | 2021-03-10 | 2021-03-17 | 7 |  |  | 3 | 3 | 0 | Functionality Document, Sequence Diagram, Workflow Diagram , UML Diagram | order Object that will be used throughout the application |  | Complete
004d | Create Referring Dr. GUI | 2021-03-10 | 2021-03-17 | 7 |  |  | 10 | 10 | 0 | Functionality Document, Sequence Diagram, Workflow Diagram , UML Diagram | Dashboard that the Reffering Dr. will see and work with |  | Complete
004e | Create view_patient method | 2021-03-10 | 2021-03-17 | 7 |  |  | 5 | 5 | 0 | Functionality Document, Sequence Diagram, Workflow Diagram , UML Diagram | ability to view existing patients |  | Complete
004f | Create new_patient method | 2021-03-10 | 2021-03-17 | 7 |  |  | 5 | 5 | 0 | Functionality Document, Sequence Diagram, Workflow Diagram , UML Diagram | ability to create a new patient |  | Complete
004g | Create patinet_lookup method | 2021-03-10 | 2021-03-17 | 7 |  |  | 5 | 5 | 0 | Functionality Document, Sequence Diagram, Workflow Diagram , UML Diagram | Ability to lookup exisitng patients |  | Complete
004h | Create new_order method | 2021-03-10 | 2021-03-17 | 7 |  |  | 5 | 5 | 0 | Functionality Document, Sequence Diagram, Workflow Diagram , UML Diagram | ability to create a new order - executed by the reffering Dr |  | Complete
004i | Create the user SuperClass | 2021-03-10 | 2021-03-17 | 7 |  |  | 3 | 3 | 0 | Functionality Document, Sequence Diagram, Workflow Diagram , UML Diagram | person object will be built upon by each of the subsequent user objects |  | Complete
004j | Give Dr Acces To patient records | 2021-03-10 | 2021-03-17 | 7 |  |  | 3 | 3 | 0 | Functionality Document, Sequence Diagram, Workflow Diagram , UML Diagram | Dr should be able to view and edit patient information along with thier medical history |  | Complete
005 | Implement Receptionist section | 2021-03-11 | 2021-03-17 | 6 |  |  | 34 | 34 | 0 | Order object, Functionality Document, Sequence Diagram, Workflow Diagram , UML Diagram | Receptionsit section | Jiovany, Ethan, Nick | Complete
005a | Create receptionist object // inherit from user | 2021-03-11 | 2021-03-17 | 6 |  |  | 2 | 2 | 0 | user object | An object to be used within the Receptionist GUI and check in / scedule appointments | Jiovanny | Complete
005b | Create schedule_order method | 2021-03-11 | 2021-03-17 | 6 |  |  | 3 | 3 | 0 | order object | schedules appointments // applys a date to the order | Nick, Jiovanny | Complete
005c | Create Receptionist GUI | 2021-03-11 | 2021-03-17 | 6 |  |  | 10 | 10 | 0 | Login Info, USer Object | View portals for all Receptionist functions | Ethan | Complete
005d | Create check_in method | 2021-03-11 | 2021-03-17 | 6 |  |  | 3 | 3 | 0 | Order Object, Patient Object | Appt Room, Team Assigned | Nick, Jiovanny | Complete
005e | Create resources objects // tools, rooms and teams | 2021-03-11 | 2021-03-17 | 6 |  |  | 4 | 4 | 0 | Modality and Team Object | Appt Room, Team Assigned | Nick, Jiovanny | Complete
005f | Create SQL query to access all schduled appointments | 2021-03-11 | 2021-03-17 | 6 |  |  | 3 | 3 | 0 | SQL query to order table | Scheduled orders from order table | Ethan, Nick | Complete
005g | Create SQL query to accesss todays appointments | 2021-03-11 | 2021-03-17 | 6 |  |  | 3 | 3 | 0 | SQL query to order table | Orders with current date appointment from order table | Ethan, Nick | Complete
005h | Create SQL query to access appointments that lack a date | 2021-03-11 | 2021-03-17 | 6 |  |  | 3 | 3 | 0 | SQL query to order table | Unscheduled orders from order table | Ethan, Nick | Complete
005i | receptionist has access to patient infomration // implement me | 2021-03-11 | 2021-03-17 | 6 |  |  | 3 | 3 | 0 | Patient Object | Patient Info, Phone Num, Allergies, Notes, Etc. | Ethan | Complete
006 | Implement technician section | 2021-03-17 | 2021-03-24 | 7 |  |  | 30 | 30 | 0 |  |  | Nick | Complete
006a | Create technician object // inherit from user | 2021-03-17 | 2021-03-24 | 7 |  |  | 5 | 5 | 0 | user object | Technician object |  | Complete
006b | Create add_image method | 2021-03-17 | 2021-03-24 | 7 |  |  | 5 | 5 | 0 | Order object and Image to be added | Updated order with Image attached |  | Complete
006c | Create remove_image method | 2021-03-17 | 2021-03-24 | 7 |  |  | 5 | 5 | 0 | Order object and image to be removed | Updated order with image removed |  | Complete
006d | Create view_image method | 2021-03-17 | 2021-03-24 | 7 |  |  | 5 | 5 | 0 | Image on selected order | Window withimage being dispalyed |  | Complete
006e | Create view_appointment method | 2021-03-17 | 2021-03-24 | 7 |  |  | 5 | 5 | 0 | Order object with appointments | List of current day's appointments |  | Complete
006f | Create submit method // sends order to radiologist | 2021-03-17 | 2021-03-24 | 7 |  |  | 5 | 5 | 0 | Order object | Updated order with notification for radiologist |  | Complete
006g | Create view_orders method | 2021-03-17 | 2021-03-24 | 7 |  |  | 5 | 5 | 0 | Order object with open status | List of open orders |  | Complete
007 | implement radiologist section | 2021-03-24 | 2021-03-28 | 4 |  |  | 29 | 29 | 0 |  |  | mikey | Complete
007a | create radiologist object //inherit from dr or user? | 2021-03-24 | 2021-03-28 | 4 |  |  | 3 | 3 | 0 | user object | Radiologist Object |  | Complete
007b | Create save_order method | 2021-03-24 | 2021-03-28 | 4 |  |  | 2 | 2 | 0 | order object | updated order object, not yet complete |  | Complete
007c | Create finalize_order method | 2021-03-24 | 2021-03-28 | 4 |  |  | 10 | 10 | 0 | order object | complete order object ready for dr report |  | Complete
007d | Create radiologist GUI | 2021-03-24 | 2021-03-28 | 4 |  |  | 5 | 5 | 0 | Login info, user object | Radiologist portal |  | Complete
007e | Create select_order method // maybe | 2021-03-24 | 2021-03-28 | 4 |  |  | 3 | 3 | 0 | all order objects | selected order object and all related info |  | Complete
007f | Radiologist can see patieint info // implment me | 2021-03-24 | 2021-03-28 | 4 |  |  | 3 | 3 | 0 | patient object | all relevant patient info |  | Complete
007g | Radiologist can write to a text box for the order // implement me | 2021-03-24 | 2021-03-28 | 4 |  |  | 3 | 3 | 0 | radiologist report | order object updated with radiologist report |  | Complete
008 | implement login dashboard and access controls | 2021-03-24 | 2021-03-28 | 4 |  |  | 8 | 8 | 0 | User object, name and password | Specific User UI and info | Nick | Complete
009 | implement SQL database and update code to incorporate | 2021-03-24 | 2021-03-28 | 4 |  |  | 15 | 15 | 0 | SQL queries | Desired info. from database tables | Ethan | Complete
010 | implement admin control | 2021-03-24 | 2021-03-28 | 4 |  |  | 10 | 10 | 0 | User objects | User child objects, and info related | Nick | Complete
011 | implement log_out method // person object | 2021-03-24 | 2021-03-28 | 4 |  |  | 3 | 3 | 0 | User object and UI display | Home window/Log in window | Nick | Complete
012 | implement allergy_conflict method | 2021-03-28 | 2021-04-06 | 9 |  |  | 2 | 2 | 0 | Allergy Variable | PopUp warning of conflict | Nick | Complete
013 | Testing | 2021-04-06 | 2021-04-28 | 22 |  |  | 10 | 10 | 0 | Test USers, Orders, Patients | Successful Completion and/or bugs | Everyone | Complete
014 | Presentation preperation | 2021-04-06 | 2021-04-11 | 5 |  |  | 5 | 5 | 0 | Project overview,Test cases, supporting documentation | Slides describing project structure and process | Jiovanny | Complete
Formulas:
Days Passed = TODAY() -[Start Date, row below]
Days Left = [End Date, row below]-TODAY()
Days Left = [End Date]-TODAY()